## Milestone Deliverables
Sl No. | Milestone | Scope & Deliverables | % | Invoicing Date (End of)
1 | Milestone 1 | TETHERAuto Base Cloud/Platform Bring-up (initial setup operational, AWS Account/Infra India Region). (DevOps) - Emulated - Vehicle Onboarding, Status, Test Data Ingestion | 5% | Mar-26
|  | Program Management, Partner Onboarding (LoI, PO) | 3%
|  | CarOTA Advance Payment | 5%
|  | TEL Program Set Up, Team Onboarding, Process Alignment | 2%
2 | Milestone 2 | Requirement Engineering (SRS) phase1 | 2.5% | Apr-26
|  | Standard Core features for Navigation (Search, Navigation, Traffic en-route) APK + Map Data (Karnataka, Maharashtra), Map SDK for Unified App, API Interfaces for Mihup, Mappls Jar | 2.5%
|  | Voice enabled invocation of Online features such as Weather, News, Cricket (LLM powered domain features) | 2.5%
To be Detailed
3 | Milestone 3 | Platform Functional Readiness (initial) - core services stable; environments configured. Demo with TCU | 2.5% | Jun-26
|  | User App & Unified App: Functional Readiness (initial) - primary flows implemented; basic integrations to platform | 2.5%
|  | Voice Engine Customizations (phase-1) - base features configured; preliminary integration hooks ** To be finalized post alignment with JSW | 2.5%
|  | App Store Customizations (phase-1) - catalog scaffolding; IVI/TBOX integration plan ** To be finalized post alignment with JSW | 2.5%
|  | TBOX customization & readiness | 2.5%
|  | OTA customization & readiness | 2.5%
|  | VE-TBOX/IVI integration (audio pipeline handshake) & App Store-IVI/TBOX integration (distribution handshake), Navigation, CarOTA | 2.5%
|  | Development Integration Validation of Onboard integrated system | 2.5%
4 | Milestone 4 | Secure connectivity proven/certificate exchange/sim flashing | 2.5% | Aug-26
|  | User App feature enhancement & readiness | 2.5%
|  | MNO Workflow Readiness + Integration to Platform/App (SIM/activation flows, telemetry pathways) | 2.5%
|  | Cloud-TBOX-IVI-AppStore end-to-end integration path established (core data and control flows) | 2.5%
|  | OTA: CarOTA Workflow Alignment + Platform Integration - workflow defined; sandbox integration validated | 2.5%
|  | Platform to User App Integration | 2.5%
|  | Development Integration Validation of Offboard integrated system | 2.5%
|  | Development Integration Validation of Offboard integrated system with Unified App | 2.5%
5 | Milestone 5 | Full E2E Functional Validation across Platform, Apps, Voice Engine, App Store, OTA, TBOX, MNO |  | Oct-26
Defect Triage & Stabilization - close criticals/blockers; regression suite established
|  | NFR Suite: Performance, reliability, scalability results documented; Security + Internal VAPT completed; Standards Adherence | 20%
6 | Milestone 6 | Environment cutover; configuration management finalization |  | Dec-26
Joint Validation (E2E) with customer/internal teams - readiness for go-live
Production Set-up - infra provisioning, monitoring/observability, incident runbooks; production readiness "Y"
|  | Production Go Live | 20%